## Initial
Created May 2020
| 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01
Part III
Write chapter 5 draft | bar: 2020-05-01 to 2020-06-01
Write chapter 6 draft | bar: 2020-06-01 to 2020-07-01
Upate thesis structure and revise intro | bar: 2020-05-01 to 2020-07-01
Part II*
Familiarise with ultrasonic trap experiment | bar: 2020-08-01
IR spectra of ice | bar: 2020-08-01 to 2020-09-01
IR spectra of ice + dust | bar: 2020-09-01 to 2020-10-01
Familiarise with MiePlot | bar: 2020-08-01 to 2020-10-01
Data analysis | bar: 2020-10-01 to 2020-11-01
Part I*
Familiarise with PAC experiment | bar: 2020-12-01
IR spectra of ASW (thermal processing) | bar: 2020-12-01 to 2021-01-01
IR spectra of ASW doped with impurities | bar: 2021-01-01 to 2021-02-01
IR spectra of ASW on 'rough' substrate | bar: 2021-02-01 to 2021-03-01
Data analysis and thesis write-up
Chapter 1 | bar: 2021-04-01 to 2021-09-01
Chapter 2 | bar: 2021-04-01 to 2021-09-01
Chapter 3 | bar: 2021-05-01 to 2021-06-01
Chapter 4 | bar: 2021-06-01 to 2021-07-01
Chapter 5 | bar: 2021-08-01
Chapter 6 | bar: 2021-08-01
Chapter 7 | bar: 2021-04-01 to 2021-09-01
*Part I and Part II are interchangeable

## Update1
Updated 22th Feb 2022
Month | 2022-01-01 |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  |  | 2022-05-01 |  |  |  | 2022-06-01 |  |  |  | 2022-07-01
Weeks | 3 _ 9 | 10 _ 16 | 17 _23 | 24 _30 | 1 _6 | 7 _13 | 14 _20 | 21 _27 | 1 _ 6 | 7 _ 13 | 14 _20 | 21 _27 | 28 _3 | 3 _ 10 | 11 _ 17 | 18 _ 24 | 25 _ 30 | 2 _ 8 | 9 _ 15 | 16 _ 22 | 23 _ 29 | 1 _ 5 | 6 _ 12 | 13 _ 19 | 20 _ 26
Code Update
Sample thickness
Data Reduction Notebook
Data Processing Notebook
Principal Component Aanalysis Notebook
Data Analysis Notebook
Data Analysis
XP-1_1
Data_Reduction
Sample Classification
Calculate sample thickness
Apply Reduction Routine 20K samples
Apply Reduction Routine Higher T samples
Data_Processing
Per sample
Between different samples
Data_Analysis
XP-1_2
Data_Reduction
Data_Processing
Data_Analysis
Thesis write-up
Chapter 1: Introducrion
Chapter 2: Theory
Chapter 3: XP-1_1 - Amorphous Solid Water
Chapter 4: XP-1_1 - ASW Crystalisation
Chapter 4: XP-1_2 - ASW + C2H6
Chapter 5: Novel expt for particle production
Chapter 6: Conclusion and Futur work
Other
Data management plan
Litterature Review
Data Analysis Strategy