## Full Gant Chart
Updated 08th September 2022
Month | 2022-10-01 |  |  |  | 2022-11-01 |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  |  | 2023-04-01 |  |  |  | 2023-05-01
Weeks | I. 3 _ 9 | II. 10 _ 16 | III. 17 _23 | IV. 24 _30 | V. 1 _6 | VI. 7 _13 | VII. 14 _20 | VIII. 21 _27 | IX. 28 _ 4 | X. 5_ 11 | XI. 12 _18 | XII. 19 _25 | XIII. 2 _8 | XIV. 9 _ 15 | XV. 16_ 22 | XVI. 23_ 29 | XVII. 30_5 | XVIII. 6_12 | XIX. 13_ 19 | XX. 20_ 26 | XXI. 27_ 5 | XXII. 6 _ 12 | XXIII. 13 _ 19 | XXIV. 20 _ 26 | XXV. 27_2 | XXVI. 3_9 | XXVII. 10_16 | XXVIII. 17_23 | XXIX. 24_30 | XXX. 1_7
Code Update
Sample thickness
Data Reduction Notebook
Data Processing Notebook
Principal Component Aanalysis Notebook
Data Analysis Notebook
Data Analysis
XP-1_1
Data_Reduction
Data_Processing
Data_Analysis
XP-1_2
Data_Reduction
Data_Processing
Data_Analysis
Thesis write-up
Chapter 1: Introducrion
Chapter 2: Method
Chapter 3: XP-1_1 - Amorphous Solid Water
Chapter 4: XP-1_1 - ASW Crystalisation
Chapter 5: XP-1_2 - ASW + C2H6
Chapter 6: Novel expt for particle production
Chapter 7: Web-site ?
Chapter 8: Conclusion and Futur work
Other
Data management plan
Litterature Review
Data Analysis Strategy

## 0.
Week 0: 12 - 16 Septembre
Action Item | Task | Importance | Status | 🔗
Progress report | Other | ⭐⭐ ⭐
Moving House | Other | ⭐
Write Blog post (conference) | Other | ⭐ | ✔
Fill conference feedback form | Other | ⭐⭐ ⭐
Write Science Page (PhD) | Other | ⭐ ⭐
Finish DR2_ASW | Code

## I.
Week 1: 3 - 9 October