## Full Gant Chart
Updated 08th September 2022
Month | 2023-01-01 |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  | 2023-06-01 |  |  |  |  | 2023-07-01 |  |  |  | 2023-08-01 |  |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  |  | 2023-11-01 |  |  |  | 2023-12-01
Weeks | 2 _ 8 | 9 _ 15 | 16 _ 22 | 23 _ 29 | 30 _ 5 | 6 _ 12 | 13 _ 19 | 20 _ 26 | 27 _ 5 | 6 _ 12 | 13 _ 19 | 20 _ 26 | 27 _ 2 | 3 _ 9 | 10 _ 16 | 17 _ 23 | 24 _ 30 | 1 _ 7 | 8 _ 14 | 15 _ 21 | 22 _ 28 | 29 _ 4 | 5 _ 11 | 12 _ 18 | 19 _ 25 | 26 _ 2 | 3_9 | 10 _ 16 | 17 _ 23 | 24 _ 30 | 31 _ 6 | 7 _ 13 | 14 _ 20 | 21 _ 27 | 28 _ 3 | 4 _ 10 | 11 _ 17 | 18 _ 24 | 25 _ 1 | 2 _ 8 | 9 _ 15 | 16 _ 22 | 23 _ 29 | 30 _ 5 | 6 _ 12 | 13 _ 19 | 20 _ 26 | 27 _ 3 | 4 _ 10 | 11 _17 | 18 _ 24 | 25 _ 31
Perso
Me
Work
Code Update
Sample thickness
DR1
DR2
DR3
DP1
DP2
DA1
DA2
Principal Component Aanalysis Notebook
Data Analysis Notebook
Data Analysis
XP-1_1
Data_Reduction
Data_Processing
Data_Analysis
XP-1_2
Data_Reduction
Data_Processing
Data_Analysis
Thesis write-up
Chapter 1 A: Introducrion
Chapter 1 B: Introducrion
Chapter 2: Method
Chapter 3: XP-1_1 - Amorphous Solid Water
Chapter 4: XP-1_1 - ASW Crystalisation
Chapter 5: XP-1_2 - ASW + C2H6
Chapter 6: Proof of concept
Chapter 7: 2nd version
Chapter 9: Conclusion and Futur work
Other
Data management plan
Litterature Review
Data Analysis Strategy
|  |  |  | Holliday |  |  | OU | Holliday |  |  |  | OU | OU | [30 empty] | Submission

## 0.
Week 0: 12 - 16 Septembre
Action Item | Task | Importance | Status | 🔗
Progress report | Other | ⭐⭐ ⭐
Moving House | Other | ⭐ | ✔
Write Blog post (conference) | Other | ⭐ | x
Fill conference feedback form | Other | ⭐⭐ ⭐ | ✔
Write Science Page (PhD) | Other | ⭐ ⭐
Finish DR2_ASW | Code

## I.
Week 1: 3 - 9 October